## Slide 1: Montana Disaster & Emergency Services Division
Public Assistance Program
Applicant Briefing FEMA-4437-DR-MT
2019 March 20 to April 10 Flooding
Declared May 24, 2019

## Slide 2: Applicant Briefing Purpose
Explain How Public Assistance Works
Identify Eligible Applicant
Identify Eligible Work
Discuss Areas of Special Concern
Discuss Funding
Answer Your Questions

## Slide 3: Governing Documents
Statue - Robert T. Stafford Act as Amended
Regulations - Code of Federal Regulations: 44 CFR Part 206 and 2 CFR Part 200
Public Assistance Program & Policy Guide (PAPPG)

## Slide 4: Acronyms
Program Delivery Manager (PDMG)
Site Inspector (SI)
Consolidated Resource Center (CRC)
Environmental Historic Preservation (EHP)
Damage, Description and Dimension (DDD)
Statement of Work (SOW)
Joint Field Office (JFO)
The Public Assistance Process
(New Model)

## Slide 5
The Public Assistance Process
(New Model)
To State
Flow Through to
Applicant
Disaster
Event
Joint PDA
Declaration
Applicant
Briefing
Notes: This slide outlines the multi-step funding process under the Public Assistance Program. The disaster event triggers the declaration process which for some applicants may or may not include a Preliminary Damage Assessment (PDA). All potential applicants will attend an Applicant’s Briefing. Applicants will submit the Request for Public Assistance which is available at the applicant’s briefing and through electronic means such as the MT DES Public Assistance Website (site is provided on the last slide of the presentation), FEMA web site or other Internet sites, to officially apply for funding. Each Applicant will be assigned a FEMA Public Assistance Coordinator (PAC) and the PAC will hold a Recovery Scoping Meeting with the applicant to begin the process of documenting disaster recovery projects. The PAC will assist the applicant in completing Project Worksheets for all projects. Project Worksheets will be approved after validation. The funding will be made available to the State. The State then disburses the funding to the applicant according to State regulations.
FEMA’s goal is to provide the funding as efficiently and expeditiously as possible to allow a quick recovery of communities affected by disaster or emergency events.

## Slide 6: PA Program Eligibility
Cost
Work
Facility
Applicant
The Public Assistance Process
(New Model)
Notes: The Stafford Act, federal regulations, and FEMA policies outline the eligibility criteria for public assistance funding. These criteria have the four components listed below.
  Applicant
  Facility
  Work
  Cost
A project can be funded only if it complies with each component. These components can be thought of as “building blocks” in which the more broadly applicable components support the others.
FEMA determines from the bottom to the top of the diagram if the various components are eligible for disaster assistance. Thus, if the applicant is not eligible, then none of the applicant’s facilities, work, or incurred costs can be eligible. Therefore, when reviewing projects for eligibility, start with the more broadly applicable components first.

## Slide 7: Applicant Eligibility
Counties, Incorporated Municipalities
Other Legally Constituted Units of Local Government
State Government Agencies and Departments
Indian/Tribes or Authorized Tribal Organizations
Certain Essential Private Non-Profits
The Public Assistance Process
(New Model)

## Slide 8: Eligibility Basic Requirements
Damage is Caused by This Disaster
Damage Must be in the Declared Area
Must be the Applicant’s Legal Responsibility
Must Meet Complete Eligibility Requirements
The Public Assistance Process
(New Model)

## Slide 9
The Public Assistance Process
(New Model)
To State
Flow Through to
Applicant
Disaster
Event
Joint PDA
Declaration
Applicant
Briefing
Submit Request
for Public Assistance

## Slide 10: Request for Public Assistance (RPA)
Initial Step in Request Process
Applicant Completes and Submits FEMA Form 90-49 (RPA)
If You Have Completed, Complete and Submit Today
All Requests Must be in by June 24, 2019
Is Not a Guarantee of Assistance Funding

## Slide 11: Applicant’s Agent Form
Identifies Single Point of Contact
Oversees Applicant’s Program Participation
Identifies Responsible Person for Record Keeping and Documentation
Complete and Return Form to State
Must be Actively Involved in the Project

## Slide 12: Duns Requirement Reminder
Data Universal Number System (DUNS) Accounts are Required by all Applicants
Provided by Dun and Bradstreet in Cooperation with Federal Government
Likely that you Already Have One
If Not, Application can be Made at:
https://iupdate.dnb.com

## Slide 13
The Public Assistance Process
(New Model)
To State
Flow Through to
Applicant
Disaster
Event
Joint PDA
Declaration
Applicant
Briefing
Submit Request
for Public Assistance
Program Delivery
Manager Assigned
Exploratory Call
Recovery Scoping
Meeting
Notes: This slide outlines the multi-step funding process under the Public Assistance Program. The disaster event triggers the declaration process which for some applicants may or may not include a Preliminary Damage Assessment (PDA). All potential applicants will attend an Applicant’s Briefing. Applicants will submit the Request for Public Assistance which is available at the applicant’s briefing and through electronic means such as the Wyoming Office of Homeland Security Public Assistance Website (site is provided on the last slide of the presentation), FEMA web site or other Internet sites, to officially apply for funding. Each Applicant will be assigned a FEMA Public Assistance Coordinator (PAC) and the PAC will hold a Kickoff Meeting with the applicant to begin the process of documenting disaster recovery projects. The PAC will assist the applicant in completing Project Worksheets for all projects. Project Worksheets will be approved after validation. The funding will be made available to the State. The State then disburses the funding to the applicant according to State regulations.
FEMA’s goal is to provide the funding as efficiently and expeditiously as possible to allow a quick recovery of communities affected by disaster or emergency events.

## Slide 14: Exploratory Call
Introduces your Program Delivery Manager (PDMG)
Damage Inventory Form Discussion
Documentation Needed for Support
Schedule Recovery Meeting
  Allow Time to Draft Damage Inventory
  Recovery Scoping Meeting Objectives Discussed

## Slide 15: Damage Inventory
Critical
Outlines ALL Damage
Can be Updated (Deadline: 60 Days Following Recovery Scoping Meeting)

## Slide 16: Recovery Scoping Meeting
Follows Applicant Briefing & Exploratory Call
PDMG Schedules with the Applicant
Establishes Partnership Between FEMA, State, and the Applicant
Designed to Focus on the Needs of each Applicant
In Depth Discussion of Damage Inventory
Notes: One-on-one meetings designed to address the specific needs of each applicant and their own project(s)

## Slide 17: Facility Eligibility
Buildings
Works (Drainage, Flood Protection)
Systems (Water, Utilities)
Roads
Bridges
Equipment
Vehicles

## Slide 18
The Public Assistance Process
(New Model)
To State
Flow Through to
Applicant
Disaster
Event
Joint PDA
Declaration
Applicant
Briefing
Submit Request
for Public Assistance
Program Delivery
Manager Assigned
Exploratory Call
Recovery Scoping
Meeting
Phase II
Intake Damage
and
Eligibility
Aanalysis
Notes: This slide outlines the multi-step funding process under the Public Assistance Program. The disaster event triggers the declaration process which for some applicants may or may not include a Preliminary Damage Assessment (PDA). All potential applicants will attend an Applicant’s Briefing. Applicants will submit the Request for Public Assistance which is available at the applicant’s briefing and through electronic means such as the Wyoming Office of Homeland Security Public Assistance Website (site is provided on the last slide of the presentation), FEMA web site or other Internet sites, to officially apply for funding. Each Applicant will be assigned a FEMA Public Assistance Coordinator (PAC) and the PAC will hold a Kickoff Meeting with the applicant to begin the process of documenting disaster recovery projects. The PAC will assist the applicant in completing Project Worksheets for all projects. Project Worksheets will be approved after validation. The funding will be made available to the State. The State then disburses the funding to the applicant according to State regulations.
FEMA’s goal is to provide the funding as efficiently and expeditiously as possible to allow a quick recovery of communities affected by disaster or emergency events.

## Slide 19: Phase II
Three Tracks
  Completed Work
  Work To Be Completed –Standard, Non-Technical
  Work To Be Completed-Specialized, Technical

## Slide 20: Categories of Work (Emergency)
Category A: Debris Removal
Category B: Emergency Protective Measures

## Slide 21: Categories of Work (Permanent)
Category C: Roads and Bridges
Category D: Water Control Facilities
Category E: Buildings and Equipment
Category F: Utilities
Category G: Parks, Recreation
Facilities and Other Items

## Slide 22: Phase II
Completed Work Track
  Document Work Completed
  Routed to CRC
  CRC Validates & Develops DDD, SOW/Costs
  CRC Reviews: QA, Insurance
  Joint Field Office Reviews: Mitigation, EHP
  PDMG Reviews DDD, SOW/Costs
  Recipient Reviews
  Applicant Reviews & Signs Project

## Slide 23: Phase II
  Site Inspection Work Order for Work to be Completed
  Site Inspection (FEMA site visit)
  PDMG & Applicant Review & Sign Off
Site Inspection Report
Damage, Description and Dimension
Standard, Non-Technical & Specialized, Technical Tracks

## Slide 24
The Public Assistance Process
(New Model)
To State
Flow Through to
Applicant
Phase III
Scoping
& Costing
Disaster
Event
Joint PDA
Declaration
Applicant
Briefing
Submit Request
for Public Assistance
Program Delivery
Manager Assigned
Exploratory Call
Recovery Scoping
Meeting
Phase II
Intake Damage
and
Eligibility
Aanalysis
Notes: This slide outlines the multi-step funding process under the Public Assistance Program. The disaster event triggers the declaration process which for some applicants may or may not include a Preliminary Damage Assessment (PDA). All potential applicants will attend an Applicant’s Briefing. Applicants will submit the Request for Public Assistance which is available at the applicant’s briefing and through electronic means such as the Wyoming Office of Homeland Security Public Assistance Website (site is provided on the last slide of the presentation), FEMA web site or other Internet sites, to officially apply for funding. Each Applicant will be assigned a FEMA Public Assistance Coordinator (PAC) and the PAC will hold a Kickoff Meeting with the applicant to begin the process of documenting disaster recovery projects. The PAC will assist the applicant in completing Project Worksheets for all projects. Project Worksheets will be approved after validation. The funding will be made available to the State. The State then disburses the funding to the applicant according to State regulations.
FEMA’s goal is to provide the funding as efficiently and expeditiously as possible to allow a quick recovery of communities affected by disaster or emergency events.

## Slide 25: Phase III
Scoping and Costing
  Decision/Option: FEMA or Applicant Develops Statement of Work/Costs?

## Slide 26: Phase III
Scoping and Costing
    If FEMA, CRC Develops SOW/Costs
      Program Compliance (Insurance,
    Mitigation, & EHP Reviews)
    - COST determined by Actual, RS Means or CEF
      PDMG Reviews & OKs
      Recipient (State) Reviews & OKs
      Applicant Reviews & OKs

## Slide 27: Phase III
Scoping and Costing
  Applicant Develops Statement of Work/Costs
  FEMA CRC Validates SOW/Costs
  QA Review

## Slide 28: Phase III
Scoping and Costing (cont.)
    Program Compliance (Insurance,
    Mitigation, & EHP Reviews)
    PDMG Reviews & OKs
    Recipient (State) Reviews & OKs
    Applicant Reviews & OKs

## Slide 29: Work Eligibility
Direct Result of the Disaster
Incident Period: March 20 – April 10, 2019
Damage Located in Declared County
Legal Responsibility of Eligible Applicant
In Active Use at Time of Disaster

## Slide 30: Work Eligibility (Con’t)
Must Follow Local/State/Federal Procument Standards – 2 CFR
Contracts Competitive Bids
Contract Must Follow Scope of Work Outlined in Project Worksheets
Reasonableness of Cost
Changes MUST be Approved in Advance
Notes: Training scheduled for April 26… Highly encourage each of you to attend, and any additional staff who might be involved in the procurement process

## Slide 31: Work Eligibility (Con’t)
Codes and Standards
  Must Apply to the Repair Work Being Performed
  Must be Reasonable, Formally Adopted in Writing and Implemented Prior to Declaration Date (May 24, 2019)
  Must Apply Uniformly to All Facilities of the Type Being Repaired
  Must Have Been Enforces When in Effect

## Slide 32: Cost Eligibility
Reasonable, Necessary and Disaster Related
Mutual Aid Agreements (Payments cannot be contingent on receiving FEMA funding)

## Slide 33: Cost Eligibility (Con’t)
Force Account Labor
  Emergency Work
    Overtime and Benefits of Regular Employees in Most Cases
    Regular, Overtime and Benefits of Temporary Hires
  Permanent Work
    Regular, Overtime and Benefits of Regular Employees and Temporary Hires

## Slide 34: Cost Eligibility (Con’t)
Equipment
  Force Account
    FEMA Rate Schedule (2017 Rates) https://www.fema.gov/schedule-equipment-rates
    Includes: Cost of Ownership, Operation, Depreciation, Maintenance, Repairs, Fuel, Lubricants, Tires and OSHA Equipment
    Standby Time is NOT Eligible
  Rented (Copy of Agreement Needed)
  Contracted

## Slide 35: Cost Eligibility (Con’t)
Material
  Used Only for Eligible Work
  Purchased for Disaster
  Used from Applicant’s Stock
  Purchase Must be Documented
  Commercial Borrow Site
    Department of Environmental Quality Approved Borrow Locations
    State Historic Preservation Approved Borrow Locations

## Slide 36: Cost Eligibility (Con’t)
Contracts
  Competitively Bid
  Reasonable Cost
  Compliant with Federal, State and Local Procurement Standards - 2 CFR
  Contractors and Sub-Contractors Eligible and NOT Debarred https://sam.gov/portal/sam

## Slide 37: Types of Project Worksheets
Minimum Project Worksheet > $ 3,200
Small Projects < $128,900
Large Projects > $ 128,900

## Slide 38: Project Worksheets
Grant Document in Which Scope of Work and Eligible Costs are Identified
FEMA’S Funding Document
Includes Review of Special Considerations
If Costs Increase from Estimates on Worksheet….

## Slide 39: Project Worksheet Formulation
Combining Associated Work Into Projects
Developing Scope of Work and Costs for the Project
Identifying Any Special Considerations

## Slide 40: Admin/Management Costs
Administrative/Management Costs:
  Properly Documented
  DAC cost up to 5% of total awards less insurance.
  Separate worksheet and will be treated as a large project with a closeout process documenting actual costs.

## Slide 41
The Public Assistance Process
(New Model)
To State
Flow Through to
Applicant
Phase III
Scoping
& Costing
Phase IV
Obligation
Disaster
Event
Joint PDA
Declaration
Applicant
Briefing
Submit Request
for Public Assistance
Program Delivery
Manager Assigned
Exploratory Call
Recovery Scoping
Meeting
Phase II
Intake Damage
and
Eligibility
Aanalysis
Notes: This slide outlines the multi-step funding process under the Public Assistance Program. The disaster event triggers the declaration process which for some applicants may or may not include a Preliminary Damage Assessment (PDA). All potential applicants will attend an Applicant’s Briefing. Applicants will submit the Request for Public Assistance which is available at the applicant’s briefing and through electronic means such as the Wyoming Office of Homeland Security Public Assistance Website (site is provided on the last slide of the presentation), FEMA web site or other Internet sites, to officially apply for funding. Each Applicant will be assigned a FEMA Public Assistance Coordinator (PAC) and the PAC will hold a Kickoff Meeting with the applicant to begin the process of documenting disaster recovery projects. The PAC will assist the applicant in completing Project Worksheets for all projects. Project Worksheets will be approved after validation. The funding will be made available to the State. The State then disburses the funding to the applicant according to State regulations.
FEMA’s goal is to provide the funding as efficiently and expeditiously as possible to allow a quick recovery of communities affected by disaster or emergency events.

## Slide 42: Phase IV
Obligation
    Recipient Approval in EMMIE
    Final Approval in EMMIE
    Obligation
    Exit Briefing

## Slide 43: Time Constraints
Emergency Work
  6 Months for Completion After Declaration
    State May Approve 6-Month Extension (for a total of 12 months)
    Need FEMA Approval for Changes in Scope of Work or Costs
      Improved Projects

## Slide 44: Time Constraints
Permanent Work
  18 Months for Completion from Declaration Date
  State May Approve 30-Month Extension
  Need FEMA Approval for Changes in Scope of Work or Costs
    Improved Projects

## Slide 45: Time Extensions
If Needed, Notify the State Immediately - Always Prior to Performance Period End
Applicants Request Must Include:
  Project Number
  Project Completion Date
  Justification
  Justifications Should be Based on Extenuating Circumstances or Unusual Requirements Beyond the Applicant’s Control

## Slide 46: Special Considerations
Insurance
  Floodplain
Hazard Mitigation (406 Mitigation)
Environmental
Historical Preservation
Additional Federal/State Compliance Requirements
All Will be Outlined in the Grant Award Agreement – Project Worksheet

## Slide 47: In Flood Zone A: “Should A, – Could A, Rule”
44 CFR Section 206.252
“Where an insurable building damaged by flooding is located in a special flood hazard zone, assistance shall be reduced, to the maximum amount of insurance proceeds that would have been received had the building and its contents been fully covered by a standard NFIP flood policy.”
If building or contents damage is in Flood Zone A, FEMA is required to deduct for flood insurance, even if the applicant doesn’t have it.
Up to $500,000 each, in building or contents damage.
Applicant receives only minimal amount, what NFIP insurance would not pay, and to receive the grant, the applicant must insure for all damage.

## Slide 48: Permits (Prior to Start of Work)
Check with Community Flood Plain Management for Requirements for Projects
Ensure Montana DNRC Consulted for Stream Related Projects
Ensure Montana Regulatory Office of USACE Consulted for Stream Related Projects
Ensure Montana FW&P Office Consulted

## Slide 49: Issues
Fill Dirt, Gravel, Rip Rap MUST Come From a DEQ/SHPO Pit OR a Commercial Source
Insurance Commitment
Track ALL Costs for Audit Purposes
Debarment of Contractors
Projects Should Not Generate Additional Income (Interest, Salvage, etc.)
Account for PW Funds Separately
Work on Major collectors not eligible

## Slide 50: Hazard Mitigation
Section 406 OF Stafford Act (Mitigation)
Cost Effective Measure that Would Reduce or Eliminate the Threat of Future Similar Damage
Considered Part of Total Eligible Cost of Repair of Damaged Facility
Only for Permanent Work Projects
Must be Approved Prior to Work Start
Notes: 406 Mitigation is associated with Public Assistance
404 Mitigation is HMGP

## Slide 51: Funding
Federal Share
  75%
  State/Local/PNPs Cost Share
    25%
If Costs Look Like They May Exceed Worksheet Estimates
  Contact MT DES

## Slide 52: Cost Share
FEMA approves an annual Public Assistance Administrative Plan developed by the State of Montana.
  Assures that Montana is prepared to coordinate and administer disaster related FEMA Grants
  Establishes general financial expectations for state, local, and federal agencies
    75% Federal Share
    25% Local Share (non-federal share)
A disaster specific Administrative Plan is also required for each declared federal disaster.
Notes: The Annual PA Administrative Plan allows local emergency managers and local elected officials with general guidelines to utilize to develop contingency strategies pre-event.
Typically, the state splits the non-federal cost share. Local agencies are responsible for committing the equivalency of their 2 mill levy, the state commits the balance.
Each disaster is unique, requiring a disaster specific administrative plan that firmly establishes the non-federal cost share.
  The disaster specific administrative plan is currently under review.
  We believe the cost share for this disaster will be in line with the general guidelines outlined above.
  However, this has not been determined – we are waiting on confirmation from the Governor’s Office of Budget and Program Planning (OBPP)

## Slide 53: Appeals
Any Determination Related to Federal Assistance May be Appealed
Appeals are Time Limited
  As Soon as Possible Following Receipt of Determination Letter
  60 Days to Submit from Receipt of Notice of the Action Which is Being Appealed
Notes: Discuss some of the potential ‘stumbling blocks’ from past experience…. What has generated appeals for Wyoming in the past… and encourage avoidance of these issues if AT ALL possible.

## Slide 54: Public Assistance Summary
Public Assistance Program Assists in the Restoration of Community Infrastructure
It is a Supplemental Cost Program (Reimbursement Basis)
Federal Share of Eligible Costs Will be Awarded to the State for Disbursement to the Applicant

## Slide 55: Documentation
More is Better, Maintain the Following:
  Request for Public Assistance
  Project Worksheets
  Labor/Payroll/Time Records
  Equipment/Materials/Supplies Records
  Contact Work Records
  Proofs of Payment (Checks, Invoices, Contracts)
  Insurance Records
  Phone Logs
  Correspondence
  Procurement Policy and Records
  Title, Leases, Permits and any Legal Records
Notes: Keep a separate file folder for each location.

## Slide 56: Closeout
Small Projects (< $128,900)
  Paid on Estimate or Actual Costs
  Applicant Certifies Completed Work (P4)
  State Performs Random Project Inspections
Large Projects (> $128,900)
  Payment Based on Actual Eligible Costs
  Final Inspection Required
  Project by Project Closeout Required

## Slide 57: Audits
Can Occur Any Time up to 3 Years After Closeout
Can be Conducted by FEMA or State
Can Result in Cost Adjustment or Disallowance
Single Audits are Required on More Then $750,000 in Federal Financial Assistance (REF: 2 CFR)

## Slide 58: Thank You
Montana Disaster & Emergency Services Division
1956 Mt. Majo Street
Fort Harrisson, MT 59636
Tim Thennis Sheri Medow
(O) 406-324-4783 (O) 406-324-4773
tthennis@mt.gov sheris@mt.gov